## Sheet1
Project Name | Car Showroom
Unit Part | ANDROID TV product Development
PIC | Rizky Lailatul Annisa
Total BreakDown | 6
Done | 66.6667
On Going | 33.3333
Meet Target | 16.6667
Delay | 83.3333
Total Days | 1.75
WorkLoad % | 146.9388
WorkLess % | -46.9388
Title | breakdown | Progress / breakdown % | Challenge | Hours | Start d/m/y H:I | Deadline | Exra time | Meet Target
UI\UX Design | layout android tv | 100 |  | 3 | 19/03/2023 | 19/03/2023 |  | 0
| Isi content layout | 50 |  | 2 | 19/03/2023 | 19/03/2023 |  | 1
| Isi content layout | 40 |  | 3 | 15/04/2023 | 15/04/2023 |  | 0
| Isi content layout | 90 |  | 3 | 24/04/2023 | 24/04/2023 |  | 0 | 32 | 0.375
| Isi content layout | 30 |  | 2 | 28/05/2023 | 28/05/2023 |  | 0
| Isi content layout | 90 |  | 1 | 29/05/2023 | 29/05/2023 |  | 0
32
32
70
8
| 2338800 | 2338800 | Total Est | 1.75 | days
116940
|  | Remider : | body email | sebelum taggal 21 |  |  | Calculate Date | -12.25
PerKatori mid time
2338800
49900
potongan promo | 116940
| 2271760 |  |  |  |  | Services |  | Help and Support |  | About Us | Payment Gateway
[6 empty] | 1 | Video On Demand | 1 | support@dens.tv | Features | 1
[6 empty] | 1 | TV Channel |  |  | Explore
[6 empty] | 1 | Social TV | 1 | Stay Social | FAQ
[6 empty] | 1 | Radio |  |  | Careers | Verified by
[6 empty] | 1 | Class Room |  |  |  | 1